## Tasks
Task ID | Project | Description | Start | End | Finished | Participants
0 | BIPV mapping | Data assessment | 2022-04-08 | 2022-05-15 | False | Frank
1 | BIPV mapping | Data assessment | 2022-04-08 | 2022-05-31 | False | Gavin
2 | BIPV mapping | Data assessment - Chinese details | 2022-05-23 | 2022-05-31 | False | Gavin
3 | BIPV mapping | Paper writing | 2022-04-08 | 2022-08-01 | False | Nilmini, Gavin, Frank
4 | Urban BIPV | Research design flowchart | 2022-04-08 | 2022-04-22 | False | Gregory
5 | Urban BIPV | Study location selection | 2022-04-08 | 2022-05-01 | False | Ingrid
6 | Urban BIPV | Solar irradiation simulation | 2022-04-08 | 2022-06-01 | False | Gavin
7 | Urban BIPV | Select 2-3 buildings/ BIPV products | 2022-04-08 | 2022-06-01 | False | Ingrid
8 | Urban BIPV | Economic assessment | 2022-04-08 | 2022-06-01 | False | Ingrid
9 | Urban BIPV | Review paper | 2022-04-08 | 2022-05-01 | False | Ingrid
10 | Product info | Stakeholder attributes | 2022-04-08 | 2022-04-22 | True | Ivan
11 | Product info | Distribution of product info | 2022-04-08 | 2022-05-01 | True | Jiaqi
12 | Product info | Provide contribution | 2022-04-08 | 2022-06-01 | False | All
13 | Product info | Wind load, wind resistance, static load, and etc. | 2022-05-20 | 2022-06-30 | FALSE | Anson
14 | STA | Internal draft | 2022-04-08 | 2022-04-26 | False | Nilmini, Pabasara, Chathuri
15 | STA | External review | 2022-04-08 | 2022-06-01 | False | Nilmini, Pabasara, Chathuri
16 | Grid impact on P2P | VCG/KDA/TR ->PV/PV+Battery | 2022-04-08 | 2022-04-22 | TRUE | Kaige
17 | Grid impact on P2P | Coorpeartive GT ->PV/PV+Battery | 2022-04-08 | 2022-04-22 | TRUE | Kaige
18 | Grid impact on P2P | Explanation of GT | 2022-04-08 | 2022-05-01 | TRUE | Kaige
19 | Grid impact on P2P | Chaperter on P2P | 2022-04-08 | 2022-05-15 | TRUE | Chathuri
20 | Grid impact on P2P | Chaperter on BIPV | 2022-04-08 | 2022-05-31 | False | Chathuri
21 | Grid impact on P2P | Two paper for GT | 2022-04-08 | 2022-06-30 | False | Chathuri
22 | Design Hub | All simulation | 2022-04-08 | 2022-04-22 | False | Sujan
23 | BIPV Enabler | Report | 2022-04-08 | 2022-04-30 | False | Pabasara
24 | BIPV Enabler | Industry workshop/travelling | 2022-04-08 | 2022-04-30 | TRUE | Rebecca
25 | HDR conference | Supports from others | 2022-05-31 | 2022-08-31 | FALSE | Gavin and all

## Publications
Task ID | Project | Description | Start | End | Finished | Participants
0 | Publication | CIB paper camera ready copy | 2022-04-22 | 2022-06-20 | FALSE | Nilmini
1 | Publication | Monte-Carlo paper | 2022-04-22 | 2022-05-30 | FALSE | Nilmini
2 | Publication | CIB paper camera ready copy | 2022-04-22 | 2022-05-20 | FALSE | Ivan
3 | Publication | Paper on Geometry information of BIPV - Ivan's part | 2022-04-22 | 2022-05-31 | FALSE | Ivan
4 | Publication | Paper on Geometry information of BIPV- full paper | 2022-04-22 | 2022-06-30 | FALSE | Ivan
5 | Publication | Paper on Non-geometry product infromation | 2022-07-01 | 2022-12-31 | FALSE | Ivan
6 | Publication | BIM paper | 2022-04-22 | 2022-06-15 | FALSE | Pabasara
7 | Publication | BIPV design methods and workflow paper - revision | 2022-04-22 | 2022-06-30 | FALSE | Pabasara
8 | Publication | Framework paper | 2022-04-22 | 2022-06-30 | FALSE | Pabasara
9 | Publication | AIRAH Conference paper | 2022-04-22 | 2022-04-27 | TRUE | Tharushi
10 | Publication | Thesis | 2022-04-22 | 2022-04-27 | TRUE | Tharushi
11 | Publication | BIPV Enabler paper structure | 2022-04-22 | 2022-05-31 | FALSE | Tharushi, Pabasara
12 | Publication | BIPV Enabler paper - whole paper | 2022-05-20 | 2022-07-31 | FALSE | Tharushi, Pabasara
13 | Publication | Case study results conference paper - Abstract | 2022-04-22 | 2022-05-31 | FALSE | Tharushi
14 | Publication | Simulation process | 2022-04-22 | 2022-04-26 | TRUE | Sujan
15 | Publication | Design Hub paper | 2022-05-20 | 2022-07-31 | FALSE | Sujan, Pabasara, Tharushi, Gavin
16 | Publication | Review paper | 2022-04-22 | 2022-05-15 | FALSE | Ingrid
17 | Publication | Fire regulations paper | 2022-04-22 | 2022-05-31 | FALSE | Frank
18 | Publication | VBA report | 2022-04-22 | 2022-05-31 | FALSE | Frank
19 | Publication | Thesis completion | 2022-04-22 | 2022-04-27 | TRUE | Gavin
20 | Publication | C4NET report | 2022-04-22 | 2022-05-02 | TRUE | Gavin
21 | Publication | Paper based on thesis | 2022-04-22 | 2022-06-30 | FALSE | Gavin
22 | Publication | CIB paper camera ready copy | 2022-04-22 | 2022-06-20 | FALSE | Kaige
23 | Publication | CIB paper camera ready copy | 2022-04-22 | 2022-06-20 | FALSE | Chathuri
24 | Publication | P2P trading paper | 2022-04-22 | 2022-06-30 | FALSE | Chathuri
25 | Publication | Comparison of game theories paper | 2022-04-22 | 2022-06-30 | FALSE | Chathuri
26 | Publication | Educational paper | 2022-07-01 | 2022-08-01 | FALSE | Chathuri
27 | Publication | Blockchain-based BIPV information system paper | 2022-07-01 | 2022-08-01 | FALSE | Chathuri
28 | Publication | Comparison of software paper - Pabasara providing information | 2022-05-20 | 2022-05-27 | FALSE | Pabasara
29 | Publication | Comparison of software paper - Whole paper | 2022-05-27 | 2023-06-30 | FALSE | Sujan
30 | Publication | Review pape | 2022-05-20 | 2022-06-15 | FALSE | Gregory
31 | Publication | Macine leanring - BIPV mapping | 2022-05-20 | 2022-08-31 | FALSE | Gregory

## Tasks for BIPV Forum
Task ID | Project | Description | Start | End | Finished | Participants
0 | Presentation slides | 1 slide on digital twin | 2022-05-20 | 2022-05-31 | FALSE | Gavin, Gregory
1 | Presentation slides | 1 slide on Bendigo project | 2022-05-20 | 2022-05-31 | FALSE | Gavin
2 | Presentation slides | 1 slide on fire safety | 2022-05-20 | 2022-05-31 | FALSE | Frank
3 | Presentation slides | 1 slide on BIPV enabler tool | 2022-05-20 | 2022-05-31 | FALSE | Tharushi
4 | Presentation slides | 1 slide on supply chain management - Blockchain | 2022-05-20 | 2022-05-31 | FALSE | Chathuri
5 | Video | BIPV Enable tool video - 2+ min | 2022-05-20 | 2022-06-05 | FALSE | Tharushi
6 | Video | Bendigo Website - 1 min | 2022-05-20 | 2022-06-05 | FALSE | Kaige
7 | Video | Gavin MATLAB - 1 min | 2022-05-20 | 2022-06-05 | FALSE | Gavin
8 | Video | Hyperledger/ Ethereum - 1 min | 2022-05-20 | 2022-06-05 | FALSE | Chathuri
9 | Video | Due on Provide material | 2022-05-20 | 2022-06-05 | FALSE | All
10 | Video | Edit video | 2022-05-20 | 2022-06-06 | FALSE | Kaige
11 | Video | Final review | 2022-05-20 | 2022-06-07 | FALSE | Rebecca
12 | logistics | Help participants to enter the building - print a list of participants and sign in sheet | 2022-05-20 | 2022-06-08 | FALSE | Nilmini, Sujan, Kaige
13 | logistics | Preparing name tags and giving them to the participants | 2022-05-20 | 2022-06-08 | FALSE | Frank, Jiatong
14 | logistics | Room management and facilitate discussion | 2022-05-20 | 2022-06-08 | FALSE | Chathuri, Tharushi
15 | logistics | Solving technical issues and provide technical support | 2022-05-20 | 2022-06-08 | FALSE | Gavin, Kaige
16 | logistics | Help when necessary | 2022-05-20 | 2022-06-08 | FALSE | Ivan, Gregory
17 | logistics | Recording whole event | 2022-05-20 | 2022-06-08 | FALSE | Jiaqi