## Sheet1
Task ID | project | description | start | end | participants
0 | BIPV mapping | Data assessment | 2022-04-08 | 2022-05-15 | Frank
1 | BIPV mapping | Data assessment | 2022-04-08 | 2022-05-31 | Gavin
2 | BIPV mapping | Paper writing | 2022-04-08 | 2022-08-01 | Nilmini, Gavin, Frank
3 | Urban BIPV | Research design flowchart | 2022-04-08 | 2022-04-22 | Gregory
4 | Urban BIPV | Study location selection | 2022-04-08 | 2022-05-01 | Ingrid
5 | Urban BIPV | Solar irradiation simulation | 2022-04-08 | 2022-06-01 | Gavin
6 | Urban BIPV | Select 2-3 buildings/ BIPV products | 2022-04-08 | 2022-06-01 | Ingrid
7 | Urban BIPV | Economic assessment | 2022-04-08 | 2022-06-01 | Ingrid
8 | Urban BIPV | Review paper | 2022-04-08 | 2022-05-01 | Ingrid
9 | Product info | Stakeholder attributes | 2022-04-08 | 2022-04-22 | Ivan
10 | Product info | Distribution of product info | 2022-04-08 | 2022-05-01 | Jiaqi
11 | Product info | Provide contribution | 2022-04-08 | 2022-06-01 | All
12 | STA | Internal draft | 2022-04-08 | 2022-04-26 | Nilmini, Pabasara, Chathuri
13 | STA | External review | 2022-04-08 | 2022-06-01 | Nilmini, Pabasara, Chathuri
14 | Grid impact on P2P | VCG/KDA/TR ->PV/PV+Battery | 2022-04-08 | 2022-04-22 | Kaige
15 | Grid impact on P2P | Coorpeartive GT ->PV/PV+Battery | 2022-04-08 | 2022-04-22 | Kaige
16 | Grid impact on P2P | Explanation of GT | 2022-04-08 | 2022-05-01 | Kaige
17 | Grid impact on P2P | Chaperter on P2P | 2022-04-08 | 2022-05-15 | Chathuri
18 | Grid impact on P2P | Chaperter on BIPV | 2022-04-08 | 2022-05-31 | Chathuri
19 | Grid impact on P2P | Two paper for GT | 2022-04-08 | 2022-06-30 | Chathuri
20 | Design Hub | All simulation | 2022-04-08 | 2022-04-22 | Sujan
21 | BIPV Enabler | Report | 2022-04-08 | 2022-04-30 | Pabasara
22 | BIPV Enabler | Industry workshop/travelling | 2022-04-08 | 2022-04-30 | Rebecca